## Sheet1
Stabilization/ Release sprints
|  |  |  | Sprint 17 |  | Sprint 18
|  |  |  | 6/03/2016 to 6/16/2016 |  | 6/17/2016 to 06/31/2016
Environment |  | No of QA |  | Week 1 | Week 2 | Week 1 | Week 2
AIX-Websphere |  | 2 |  | 03rd June to 09th June | 10th June to 16th June | 17th June to 23rd June | 24th July to 30th June
| Unique | Total | Modules
| 19 | 24 | CreatePromotion | 19 |  |  | 5
| 31 | 15 | EditPromotion | 10 |  |  | 5
| 15 | 25 | AddProducts | 25
| 11 | 21 | CopyPromotion | 11 |  |  | 10
| 21 | 26 | OfferStateControl | 21 |  |  | 5
| 49 | 108 | Offer Import | 49 |  | 49 | 10
| 9 | 14 | Offer Level UDC's | 9 |  |  | 5
| 8 | 12 | Product Search Filter by Attribute |  | 8 |  | 4
| 158 | 233 | Promotions Worksheet | 28 | 60 | 70 | 75
| 39 | 39 | Search Promotions |  |  | 39
| 17 | 17 | Security |  |  | 17
| 14 | 14 | System Performance |  | 14
| 139 | 190 | Walmart TestCases | 40 | 85 | 25 | 40
| 3 | 6 | EditWorksheet |  | 3 |  | 3
| 3 | 3 | PromoDFU UDCs | 3
Total | 536 | 747 |  | 215 | 170 | 200 | 162
|  |  | No of Working days | 5 days | 5 days | 5 days | 5 days
|  |  | Approx No of cases executed perday | 43 | 34 | 40 | 32.4
High Importance Cases

## Sheet2
Sprint 18
[8 empty] | 10th June to 16th June | [6 empty] | 6/17/2016 to 06/23/2016 | [6 empty] | 6/24/2016 to 06/30/2016
| 2016-06-03 | 2016-06-04 | 2016-06-05 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11 | 2016-06-12 | 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17 | 2016-06-18 | 2016-06-19 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-25 | 2016-06-26 | 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30
Cases executed by Automation
Per day TC by QA
Per day TC by Non QA
Per day Executed
Backlog